SOCIALSPHEAR

Engineering Roadmap

12 Milestones  |  9-Month Plan  |  June 2026  |  Confidential

# Overview

This roadmap covers 12 engineering milestones from initial project setup to the launch of P2 features. Each milestone has a clear goal, owner, and deliverable list. The 9-month timeline targets a public launch at Month 5 and full P1+P2 feature parity by Month 9.

| Milestone | Name | Month | Track | Status |
| --- | --- | --- | --- | --- |
| M1 | Foundation and Infra Setup | 1, Week 1–2 | Infrastructure | Not Started |
| M2 | Social Account OAuth | 1, Week 3–4 | Feature | Not Started |
| M3 | Content Composer | 2, Week 1–2 | Feature | Not Started |
| M4 | Scheduling Engine | 2, Week 3–4 | Feature | Not Started |
| M5 | Content Calendar | 3, Week 1 | Feature | Not Started |
| M6 | AI Caption and Hashtags | 3, Week 2 | AI | Not Started |
| M7 | Analytics Dashboard | 3, Week 3–4 | Feature | Not Started |
| M8 | Team and Approval Workflow | 4, Week 1 | Feature | Not Started |
| M9 | Billing and Closed Beta | 4, Week 2–3 | Launch | Not Started |
| M10 | Public Launch | 5, Week 1 | Launch | Not Started |
| M11 | P1 Feature Sprint | 5–6 | Feature + AI | Not Started |
| M12 | P2 Feature Sprint | 7–9 | Growth | Not Started |

# Phase 1 — Build (Months 1–4)

| M1 Month 1, Week 1–2 | Foundation and Infrastructure Setup Goal: Zero-to-running local dev environment and cloud infrastructure |
| --- | --- |
| Owner: Dipesh + Full-Stack Engineer 1 | - Initialise Turborepo monorepo with pnpm workspaces - Scaffold Next.js 15 app with App Router, TypeScript, Tailwind CSS v4, Shadcn/UI - Scaffold NestJS app with TypeScript, tRPC adapter, Swagger - Create packages/types, packages/db, packages/ui in monorepo - Set up Prisma schema v1 — User, Workspace, TeamMember tables - Provision Supabase project — connect Prisma, run initial migration - Set up Upstash Redis — connect to NestJS - Integrate Clerk — sign-in, sign-up pages, ClerkGuard NestJS middleware - Set up GitHub repository with branch protection rules - Configure GitHub Actions — lint, typecheck, test, build pipeline - Deploy Next.js to Vercel (preview and production environments) - Deploy NestJS to Railway (staging and production environments) - Set up Sentry for frontend and backend error tracking - Set up PostHog for product analytics - Write project README and local setup documentation |

| M2 Month 1, Week 3–4 | Social Account OAuth Connections Goal: Users can connect and manage their social media accounts |
| --- | --- |
| Owner: Full-Stack Engineer 1 + Backend Engineer | - Create SocialAccount Prisma model — encrypted token fields - Implement AES-256-GCM token encryption and decryption service - Build OAuth 2.0 flow for: Instagram, Facebook, Twitter/X, LinkedIn, TikTok - Build OAuth 2.0 flow for: Pinterest, YouTube, Google Business, Threads, BlueSky - Create social-accounts NestJS module with connect/disconnect/refresh endpoints - tRPC router: socialAccounts.connect, disconnect, list, getHealth - Build account health checker — detect expired and expiring tokens - Implement Temporal TokenRefreshWorkflow — auto-refresh 24h before expiry - Frontend: Connected Accounts settings page with add/remove/status UI - Frontend: OAuth redirect handler and success/error states - Handle platform API rate limits — per-platform request throttling - Write integration tests for each platform OAuth flow (mocked with MSW) |

| M3 Month 2, Week 1–2 | Content Composer Goal: Users can create, preview, and draft multi-platform posts with media |
| --- | --- |
| Owner: Frontend Engineer + Full-Stack Engineer 1 | - Build rich text editor component (Tiptap or custom contenteditable) - Real-time character counter per selected platform with limit enforcement - Platform selector — choose 1 or many platforms per post - Per-platform content overrides — different caption per platform if needed - Media upload: drag-and-drop, file picker — images and videos - R2 presigned upload URL generation via NestJS media module - Cloudinary integration — auto-transform uploaded media per platform format - Multi-image carousel support for Instagram and LinkedIn - Platform preview panel — live preview of how post looks on each platform - Hashtag input with typeahead suggestions (Typesense-backed) - Draft auto-save — Zustand draft store, debounced persistence to DB every 30s - Posts tRPC router: create, update, saveDraft, deleteDraft - Frontend: Composer page layout with editor, preview, and AI sidebar panels - Playwright E2E: create post, upload image, preview, save draft |

| M4 Month 2, Week 3–4 | Scheduling Engine — BullMQ + Temporal Goal: Posts publish reliably at the scheduled time with retry and alerting |
| --- | --- |
| Owner: Backend Engineer + Full-Stack Engineer 2 | - Set up BullMQ with Upstash Redis — all 6 queues defined - Build scheduler NestJS module — PostSchedulerService - Build publisher NestJS module — separate workers per social platform - Implement platform publisher adapters: Instagram Graph API, Facebook, Twitter/X v2 - Implement platform publisher adapters: LinkedIn, TikTok, Pinterest, YouTube, others - Post state machine — DRAFT to SCHEDULED to QUEUED to PUBLISHING to PUBLISHED or FAILED - BullMQ retry logic — 3 retries with exponential backoff per queue spec - Temporal ScheduledPostWorkflow — wait, dispatch, monitor, analytics trigger - Temporal RecurringPostWorkflow — clone and reschedule on completion - Failed post alert — Socket.io event and email notification via Resend - PostJob table population — one row per platform per post, status tracking - BullMQ dashboard (Bull Board) — internal admin view of queue health - Stress test: schedule 1,000 posts simultaneously, verify under 1% failure rate - Playwright E2E: schedule post, verify PostJob status, mock delivery success |

| M5 Month 3, Week 1 | Content Calendar Goal: Users see all scheduled posts in a visual calendar and can drag to reschedule |
| --- | --- |
| Owner: Frontend Engineer + Full-Stack Engineer 1 | - Month view calendar — all scheduled posts per day, colour-coded by platform - Week view calendar — hourly slots with post cards - Day view calendar — full post details per slot - Drag-and-drop rescheduling — update scheduledAt on drop with Zustand optimistic update - Platform filter — show and hide specific platforms - Status filter — scheduled, published, failed, draft - Post quick-preview popover on hover — content, platform, scheduled time - Post edit — click post to open in composer - Bulk select — select multiple posts, bulk reschedule or delete - Calendar export — PDF via browser print, CSV via tRPC endpoint - Virtual rendering for calendars with 500+ posts (TanStack Virtual) - Responsive: full calendar functionality on mobile with touch drag-and-drop |

| M6 Month 3, Week 2 | AI Caption Generator and Hashtag Engine Goal: Users generate platform-optimised captions and hashtags with one click |
| --- | --- |
| Owner: AI/ML Engineer + Frontend Engineer | - NestJS AI module — CaptionGeneratorService, HashtagService, BrandVoiceService - Integrate Vercel AI SDK with Anthropic Claude API (claude-sonnet-4-6) - Caption generation tRPC procedure — topic, tone, platform, language inputs - Streaming response — stream caption tokens to frontend via tRPC subscription - Platform-specific formatting — auto-trim to character limit, adjust tone - Tone selector — professional, casual, witty, inspirational, educational - Language support — 20 languages via Claude API - Hashtag generation — suggest 5–30 relevant hashtags per topic - Regenerate flow — Give me 3 alternatives — stream 3 options simultaneously - Brand voice training UI — upload 5–20 example posts in AI Studio - Brand voice embedding pipeline — pgvector storage, cosine similarity retrieval - AI credit system — deduct credits per generation, check plan limits - Credit usage display — current usage vs plan allowance in header - Frontend: AI assist sidebar in composer — caption, hashtags, tone, language |

| M7 Month 3, Week 3–4 | Analytics Dashboard Goal: Users see post and account performance metrics with date range filtering |
| --- | --- |
| Owner: Backend Engineer + Frontend Engineer | - Provision ClickHouse Cloud instance — post_metrics and account_snapshots tables - Analytics ingestion worker — BullMQ analytics:ingest queue fetches metrics 1h after publish - Platform analytics adapters — pull engagement data from each social platform API - ClickHouse query service — NestJS AnalyticsQueryService - tRPC analytics router: getPostMetrics, getAccountMetrics, getTopPosts, exportCSV - Dashboard overview: total reach, impressions, engagement rate (last 30 days) - Top posts ranked by engagement rate — filterable by platform and date range - Follower growth chart — line chart per platform (Recharts) - Engagement rate over time — area chart with platform overlay - Platform comparison — bar chart comparing reach across platforms - Post-level breakdown — click any post to see full metrics history - Date range filter: 7d, 30d, 90d, custom with date picker - CSV export — all metrics for selected date range as downloadable file - Mobile-responsive charts with touch-friendly interactions |

| M8 Month 4, Week 1 | Team and Approval Workflow Goal: Teams can collaborate with roles, invites, and a content approval flow |
| --- | --- |
| Owner: Full-Stack Engineer 1 + Full-Stack Engineer 2 | - TeamMember Prisma model — workspace_id, user_id, role, invite_status - tRPC workspace router: invite, acceptInvite, updateRole, removeMember, listMembers - Role-based access control middleware — Owner, Admin, Editor, Viewer permissions - Email invite flow — Resend sends invite link, user clicks to join workspace - Approval workflow: Editor submits post, Admin receives notification, approve or reject - Approval status on PostJob — none, pending, approved, rejected - Scheduled posts blocked from BullMQ queue until approval_status is approved - Rejection reason — Admin adds comment on rejection, Editor notified - Activity log — append-only log of all post and member actions in workspace - Frontend: Team settings page — member list, invite modal, role dropdowns - Frontend: Approval queue view — pending posts for Admin review - Frontend: Notification bell — real-time Socket.io count of pending approvals - Frontend: Activity log page — filterable by user, action, date |

# Phase 2 — Launch (Months 4–5)

| M9 Month 4, Week 2–3 | Stripe Billing and Closed Beta Goal: Platform is billable and 50 beta users are actively using it |
| --- | --- |
| Owner: Full-Stack Engineer 2 + Dipesh (GTM) | - Create Stripe products and prices for all 5 plans (Free, Creator, Pro, Agency, Enterprise) - NestJS billing module — CheckoutService, SubscriptionService, WebhookService - Stripe Checkout integration — upgrade flow from within dashboard - Stripe webhook handler — subscription created/updated/cancelled updates workspace.plan - Plan enforcement middleware — check plan limits before AI generation or channel add - Billing portal — customers manage their subscription via Stripe Customer Portal - Usage-based credit tracking — AI credits consumed vs plan allowance in Redis - Frontend: Pricing page at /pricing — all plans with feature comparison table - Frontend: Upgrade prompt modals — shown when user hits plan limit - Frontend: Billing settings page — current plan, usage, upgrade/downgrade button - Recruit 50 beta users from Twitter/X, LinkedIn, and creator communities - Beta feedback form in-app — PostHog survey triggered after 3rd post scheduled - Weekly beta user feedback calls — Dipesh leads, product issues logged in GitHub |

| M10 Month 5, Week 1 | Public Launch Goal: SocialSphear is publicly available with paying customers and press coverage |
| --- | --- |
| Owner: Dipesh (GTM) + All Engineers | - ProductHunt launch — prepare assets, schedule launch, coordinate upvote campaign - Launch blog post — Why we built SocialSphear on socialsphear.com/blog - Twitter/X launch thread — Dipesh personal account, behind-the-scenes build story - YouTube demo video — 5-minute walkthrough of scheduling flow and AI features - Landing page — hero, features, pricing, testimonials, FAQ - SEO foundation — meta tags, Open Graph, sitemap.xml, robots.txt, Core Web Vitals green - Affiliate programme setup — 30% recurring commission via Rewardful - Founding Member offer — first 100 customers get 50% off for life - Customer success playbook — onboarding email sequence (5 emails over 14 days) - Help documentation — socialsphear.com/docs with guides for all core flows - Status page — status.socialsphear.com (Better Uptime) - Support inbox — Intercom live chat on dashboard, support@socialsphear.com - Agency cold outreach — 200 LinkedIn DMs to social media agency founders - Press outreach — TechCrunch, IndieHackers, Hacker News Show HN |

# Phase 3 — Growth (Months 5–9)

| M11 Month 5–6 | P1 Feature Sprint Goal: 8 high-demand features ship based on beta user feedback |
| --- | --- |
| Owner: All Engineers | - AI image generation — fal.ai Flux integration, 512px and 1024px options - Image generation UI — prompt input, style options, generated image gallery in composer - Link-in-bio page builder — custom landing page at socialsphear.com/u/username - Instagram grid preview — virtual grid showing how scheduled posts change the feed - Social inbox — unified comment and DM feed from all connected platforms - Social inbox reply interface — reply to comments inline with platform preview - White-label PDF reports — agency plan, custom logo and brand colours, client name - Report builder — select metrics, date range, platforms, generate PDF via Puppeteer - RSS auto-posting — connect blog RSS, new posts auto-drafted for scheduling - Bulk CSV scheduling — upload CSV with content, dates, platforms, media URLs - Browser extension — Chrome and Firefox, clip content to drafts queue from any webpage - Canva integration — OAuth connect, import design directly to composer |

| M12 Month 7–9 | P2 Feature Sprint Goal: Advanced features unlock agency and enterprise market segments |
| --- | --- |
| Owner: All Engineers + DevOps | - Social listening — keyword and brand mention monitoring across platforms - Listening alert engine — email and Slack notifications for negative sentiment spikes - Competitor tracking — track up to 5 competitor accounts, follower growth, posting frequency - AI content planner — LangChain agent generates full month content calendar - Content plan UI — AI-suggested posts loaded into calendar, editable before scheduling - Video caption generation — auto-transcribe video uploads using Whisper API - TikTok native auto-publish — full Content Posting API (no notification workaround) - Instagram Reels native auto-publish — using Reels Publishing API - Zapier integration — publish SocialSphear Zapier app to marketplace - Make integration — SocialSphear module with trigger and action support - Public REST API — documented at api.socialsphear.com, OAuth 2.0, rate limited - API key management UI — create, revoke, view usage for developer API keys - Slack notification integration — post publish confirmations and approval requests - SOC 2 Type I preparation — engage auditor, implement controls, gather evidence |

# Appendix: Engineering Standards

## Definition of Done

- Feature has passing unit tests (Vitest) with over 80% coverage of new code

- E2E test written in Playwright covering the happy path

- TypeScript strict mode — no 'any' types, no type assertions without comment

- Reviewed and approved by at least one other engineer via GitHub PR

- Deployed to staging and smoke tested manually

- PostHog event tracking added for key user actions in the feature

- Documentation updated in /docs if feature changes a user-facing flow

## Engineering Principles

- Ship working software over perfect software — get features to beta users fast

- TypeScript everywhere — if it does not have types, it does not ship

- Test what matters — E2E for critical paths (scheduling, billing), unit for business logic

- Database migrations are forward-only — no destructive migrations without data backfill

- Feature flags via PostHog — all major features gated behind a flag before full rollout

- Error budgets — if post delivery success rate drops below 99.5%, halt all non-critical work

## Team Hiring Timeline

| Role | Hire By | Stack | Salary Range (USD) |
| --- | --- | --- | --- |
| Product Designer (UI/UX) | Month 1 | Figma, design systems, user research | $70k–$90k |
| Full-Stack Engineer 1 | Month 1 | Next.js, NestJS, TypeScript, Prisma | $90k–$120k |
| Backend Engineer | Month 2 | NestJS, BullMQ, Temporal, ClickHouse | $90k–$120k |
| Frontend Engineer | Month 2 | Next.js, Tailwind, Shadcn, Recharts | $80k–$110k |
| Full-Stack Engineer 2 | Month 3 | Next.js, NestJS, TypeScript | $90k–$120k |
| AI/ML Engineer | Month 3 | LangChain.js, Vercel AI SDK, vector DBs | $110k–$140k |
| DevOps Engineer (contract) | Month 2 | Railway, Cloudflare, GitHub Actions, Docker | $50/hr |